## Slide 1: Auto-Park for Social Robots
By Team Daedalus

## Slide 2: Outline
Work Breakdown Structure
Status
Schedule
Unforeseen Challenges
FVE Progress
Risk Management

## Slide 3: Work Breakdown Structure
Validate
Validate
Validate
APfSR
P2P Com.
App
Sensing and Perception
Literature Study
Subsystem Integration
Bluetooth
Algorithm
GUI
Phone ↔ Laptop
Phone ↔ ROS
Mobile Platforms
Literature Study
Hardware
Hardware
Network
Acquire
Assemble and Mount
Power and Actuation
Design
Functions
Test
Test
Literature Study
SBC & Arduino Mega
Test
Acquire
Test
Test
Acquire
Send Serial Commands
Test
SBC and Comm.
Define Serial Protocol
Configure XBees
Test
MP & Subsystems
Validate
Interface Arduino w/Sensors
Odroid XU4 w/Kinect
Emergency Node
Kinect Obstacle Detection
Project Management
Test 1D Locomotion
Test
Validate

## Slide 4: Current System Status
Auto Park for Social Robots
Mobile Platform
Navigation and Control
Sensing and Perception
Android App
Development
Communication
System

## Slide 5: ROS Framework
Decision Unit
Mobile App Node
Collaboration Node (Send/Receive Data between SBCs)
Data Analysis Node (Parsing Received Occupancy Map)
Locomotion Node (Control Oculus Prime)
Emergency Node (IR-Arduino Nano)
Obstacle Detection Node (Kinect)

## Slide 6: Android App Development
Application GUI
Send Serial Messages
Android Application GUI

## Slide 7: Communication System
Literature Survey
Hardware Procurement
Preliminary Testing
Create ROS Collaboration Node

## Slide 8: Communication Architecture
Smartphone
ODroid XU4
ODroid XU4
ODroid XU4
XBee Pro 900
Bluetooth 4.0
XBee Pro 900
XBee Pro 900
Freq : 902 - 928 Mhz
Indoor Range: 450 ft
Data Rate: 156.25 kbps Topology : Mesh
Antenna Transmit Power 50mW

## Slide 9: Mobile Platform
Literature Survey
Assembled Mobile Platform

## Slide 10: Sensing and Perception
Literature Survey
Kinect Libraries Installation
Obstacle Definition
IR Close Range Obstacle Detection
Kinect Obstacle Detection

## Slide 11
Unfiltered and Dense Point Cloud Data
Dense Point Cloud Data of a Board
Down-Sampled Point Cloud of a Board
Point Cloud of a Person Holding Cup

## Slide 12: Navigation and Control
Literature Survey
MALG-PCB Software Familiarization
Locomotion Arduino Node
MALG PCB

## Slide 13: Schedule

## Slide 14: Schedule

## Slide 15: Unforeseen Challenges
Bumps | Technical Challenge | Delay | Lack of Progress
32-64 bit package compatibility | √ | √ | 
SBC Setup |  | √ | 
Setting up Kinect | √ |  | √
Mobile Platform Shipment |  | √ | 
PCB – PDB vs. IR |  | √ | √

## Slide 16
It’s not you, it’s me.

## Slide 17: Fall Demo 1
Android Application
SBC
Arduino
LED Control
Motor Control + Encoder Feedback
Bluetooth
Serial
Start/Stop
Motion Control
Position Feedback
Park/ Unpark
Status
ETP/ ETA

## Slide 18: Fall Demo 1
Task | Success Criteria | Requirements Validated | Progress
“Park” command sent to the mobile platform using the Android app | LED blinks to indicate command received | MF.1 | Command sent to laptop via Bluetooth
Vehicle begins locomotion upon receiving the command | Vehicle moves forward and turns as required to reach destination | MF.10 | Command received and interpreted
“Return” command sent to the mobile platform via the Android app | Vehicle moves forward, backward, and turns to reach destination | MF.1, MF.10 | Command sent to laptop via Bluetooth

## Slide 19: Fall Demo 2
Android Application
SBC
Arduino
LED Control
Motor Control + Encoder Feedback
Bluetooth
Serial
Start/Stop
Motion Control
Position Feedback
Park/ Unpark
Status
ETP/ ETA
SBC
Sends Request
Kinect
IR - Arduino Nano
Obstacle Detection
Direction

## Slide 20: Fall Demo 2
Task | Success Criteria | Requirements Validated | Progress
“Park” command sent to the mobile platform using the Android app | LED blinks to indicate command received | MF.1 | Command sent to laptop via Bluetooth
Navigation direction set from second SBC | Platform receives destination | MF.2, MN.2, DN.1, MN.5 | XBees share data between laptops XBees can join and drop No changes to infrastructure
Platform begins locomotion upon receiving the command | Vehicle moves forward and turns as required to reach destination | MF.10 | Serial Protocol defined
While navigating to the spot, the vehicle will detect an obstacle and stop within a safe distance of the obstacle | Vehicle does not collide with obstacle | MF.8, MN.6 | IR works Working on Kinect

## Slide 21: Risk Management
ID | Description | Owner | Area of Impact | Mitigation Plan | Status
1 | No Mobile Platform | Mohak | Technical Schedule Cost | Purchase test platform Email list of MPs to sponsor Meet with Sponsor | Resolved
2 | Inadequate Mobile Platform | Shivam | Technical | Review platform needs Only select adequate platform | In Progress
3 | Unsuitable Smartphone Interface | Dorothy | Technical Programmatic | Frequent and extensive testing | Open
4 | Subsystem Incompatibility | Pranav | Technical Schedule Cost Programmatic | Research on ROS to ensure compatibility Software architecture to ease integration Carry out low level cross compatibility tests | In Progress

## Slide 22: Risk Management
ID | Description | Owner | Area of Impact | Mitigation Plan | Status
5 | Too Many Requirements | Shivam | Schedule Programmatic | Trimmed requirements Separated mandatory from desirable Appointed PM Begin big weekly scrums Created Kanban cards | Resolved
6 | Inaccurate Parking Lot and Obstacles | Richa | Programmatic | Analyze parking lots IRL Scale to match mobile platform | Open
7 | ROS Framework | Pranav | Technical | Arduino/ROS testing Android/ROS testing ROS-ROS serial communication | In Progress
8 | SBC and Platform Incompatibility | Mohak | Technical Schedule Cost Programmatic | Test SBCs from inventory Contact manufacturer Order new, compatible SBCs Work-around with 32-bit SBCs | In Progress

## Slide 23: Risk Management

## Slide 24: Thank you!
Questions?