## Slide 1: FlySense Augmented Reality FPV assisted navigation (applied to a helicopter)
Team C
October 2017
Shivang Bhaveja
Harikrishnan Suresh
Nick Crispie
Joao Fonseca
Sai Nihar Tadichetty

## Slide 2
Flash update
Feature | Achievements this week | Target for next week
UI/UX | Interface with Jetson drafted Epson BT-300 tested vs Hololens Lighter and easier to wear Better under strong direct lightning Images are stationary Sound in Android 2D sound library identified 2 mics noise cancellation identified Offline speech recognition library identified Confirmed that 3D sound does not work with beep sounds (only polyphonic signals) | Testing Android sound libraries Initial mock-ups of HUD With artificial horizon based on head pose and dummy input from onboard computer)
Sensing | Range extended (from 5 to 20 meters) Ghost image removed for slowing moving objects 3D artefacts removed from the floor | Convert Octomap to Gridmap (ethz-asl/grid_map) Convert from PointCloud to Gridmap (Air Lab Code) Apply Edge detection filter to Grid map
System Int. & Testing | Jetson ATK setup with Octomap and Rviz Octomaps generated for the 16 channel Velodyne tested in the lab | Validation of the interface AR - Jetson Octomaps generated for the 64 channel Velodyne data from NEA
Procurement and project management | Procurement of Epson BT-300 finalised | Design Fall Validation Experiment in detail
Updated

## Slide 3: Second attempt at 3D mapping for slowly moving obstacles was successful
VELODYNE TESTING
Objective of test:
  Test octomaping algorithm for moving obstacles
Achievements
  Range extended (from 5 to 20 meters)
  Ghost image removed for slowing moving objects
  3D artefacts removed from the floor
Next steps
Achievements

## Slide 4: In parallel with the simplification of our requirements, we have reorganized the workflow in order to minimize rework
FlySense
Least resistance path
Sensors in a box
Quadcopter
Simulation (online)
Helicopter
FlySense
A
B
C
D
Initial Approach
FVE
Simulation (offline flight dataset)
Quadcopter
Helicopter
A
B
C
D
Current Approach
Sensors in a box
?
?

## Slide 5: Under the new approach, we are currently on schedule (detail in backup)
Draft schedule (subsystem/system level)
Tracks | PR 1 20 Oct 2017 | PR 2 27 Oct 2017 | PDR 31 Oct | PR3 Nov 10 | PR4 Nov 22 | PR5 Nov 30 | PR6 Dec 7 | Critical Review Dec 14
UI/UX | First visualization of sensor suite Specification to onboard computer | Head tracking for artificial horizon | Mock-up of HUD | Mock-up of BDV | Mock-up of sound | HUD and Bird’s Eye View with NEA dataset | Additional testing and refinement | Planning for next phase
Sensing | Point cloud of Lidar Data set | Onboard obstacle map generation | Interface to AR headset | Obstacle map with NEA flight dataset | Interface to AR |  |  | 
System Int. & Testing | Procurement of Epson BT-300, Velodyne and Jetson | Design of Fall verification experiment | Integration and testing of HUD |  | Integration and testing for Fall Validation Experiment (HUD, BDV, Sound) |  |  | 
✔
✔
✔
✔
✔
Note: Either Audio Warnings or Speech Recognition for Fall Validation.

## Slide 6: We are currently deploying mitigation actions with owners to address the key risks identified
4 Major Risks and mitigation strategy
Probability of occurrence
Severity
Octomap (Shivang/Hari)
  Octomap cannot process 3 LiDAR datasets real time
    Segment point cloud
    Process only 1 velodyne
AR Headset (Nihar)
  AR headset motion sickness
    Set focal distance to 20 meters
    Train pilots extensively
UI/UX voice commands (Joao)
  Voice commands do not work
    Bird’s eye pops-up automatically
    2 microphones for noise cancellation + Android offline library
Quadcopter not available (TBD)
  Too much time to make drone test
    Use NEA drone (from start)
    Drop Quadcopter from scope
Three major risks identified
Chart: 
| 8 | 8 | 8 | 7 | 5 | 5 | 5 | 5 | 5 | 10 | 9 | 4 | 4 | 4 | 6 | 5 | 5 | 4 | 5 | 3 | 9 | 4 | 2 | 2 | 5 | 4 | 2 | 2 | 4
16 17 18 5 1 11 13 14 23 20 12 4 9 28 21 3 22 26 27 2 15 19 10 29 24 7 25 6 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 7 | 10 | 10 | 10 | 8 | 8 | 8 | 8 | 7 | 8 | 4 | 6 | 8 | 8 | 5 | 5 | 7 | 5 | 3
1,2,3
4
Note: 29 risk identified so far
Preliminary

## Slide 7
NEW END-DELIVERABLE
Scale = 300 ft
BV
HUD
BV
HUD
100
95
90
80
Torque %
-20 -10 0 10 20 30
Heading
1,150
1,100
1,000
950
Alt (ft)
ASL
AGL
BV
HUD
Updated
Thank You!

## Slide 8
Backup

## Slide 9
 | Sensing | UI/UIX | FlySense Validation
Algorithm | 3D mapping Flight envelope 2D obstacle map | Sound warnings Speech recognition (with noise cancellation) | NA
Software | Interface to AR Interfacing with sensors Mapping implementation Bird’s eye view image generation | Generate Sound Warnings Render Bird’s Eye view Render Std Instruments User Interface (Buttons, pop-up, speech) | NA
Hardware (procure, setup, test) | PDR LIDAR Jetson INS-GPS | Augmented Reality Headset up and running (Epson) | Flying Quadcopter with sensors Jetson to Helicopter computer
Integration | Jetson -> AR Jetson+LIDAR Jetson+GPS-INS Jetson+LIDAR+GPS/INS+PDB | Jetson communication protocol AR -> Jetson | Integrate with NEA LIDAR Datasets Integrate with Quadcopter Integrate with NEA Helicopter
Testing | LIDAR Static LIDAR Moving GPS/INS test PDB test | AR connected with PC AR connected with Jetson | Test with NEA LIDAR dataset Test with Quadcopter Test with NEA Helicopter
NEW Work Breakdown Structure

## Slide 10
DETAILED WBS SCHEDULE (1/2)
Updated

## Slide 11
DETAILED WBS SCHEDULE (2/2)
Updated

## Slide 12: Previous features were segmented based on feedback gathered so far
Functional requirements were trimmed to address
FlySense AR Interface
Standard Instruments
Bird Eye View
Map and path planning
First Person View Overlay
Time
0
1
2
3
4
What pilots have seen before
What pilots are looking for today
What pilots do not yet understand but will be “the future”
Quick shortcuts interface additional to the AR standard interface needed
First Year (MRSD Project)
“Auto Emergency Braking” possible as it becomes transparent to the pilot
3D Sound can be added to further aid the pilot locating the obstacle